## Function Completion
ifroglab function | Status | lora_util function
__init(self) | Done | __init__(self)
serial_allPorts(self) | Done | global listPorts(self)
Fun_CRC(self, data) | Done | __calCRC(self, data)
serial_ports(self) | Deleted
FunLora_init(self) | Deleted
FunLora_initByName(self, i_portPath) | Done | openPort(self, portPath)
Fun_OS(self) | Done | findLoRa(self, ports)
FunLora_ChipSendByte(self, array1) | Done | sendByteToChip(self, data)
Fun_ser_Write(self, array1) | Done | serialWrite(self, data)
FunLora_close(self) | Done | serialClose(self)
FunLora_0_GetChipID(self) | Done | getLoRaID(self)
FunLora_0_GetDeviceID(self) | Deleted
FunLora_1_Init(self) | Done | resetLoRa(self)
FunLora_2_ReadSetup(self) | Done | getStatus(self)
FunLora_3_Rx(self) | Done | setRx(self)
FunLora_3_Tx(self) | Done | setTx(self)
FunLora_6_readPureData(self) | Done | get(self)
FunLora_7_readCounter(self) | Done | readCounter(self)
FunLora_5_write16bytesArrayString(self, data_array) | Done | put(self, content)
FunLora_5_write16bytesArray(self, data_array) | Deleted
FunLora_5_write16bytes(self, data_array) | Deleted
Fun_ArrayCopy(self, A) | Deleted | Replace with copy.deepcopy() | Not implement
Fun_ArrayToString(self, A) | Deleted
Fun_ArrayIsSame(self, A, B) | Deleted | Replace with A == B | Not implement
Fun_ArrayIsSame_thread(self, q, A, B) | Deleted | Replace with A == B | Not implement
FunLora_5_writeString(self, iString) | Done | write(self, content)
FunLora_5_write(self, data_array) | Deleted
FunLora_5_read_v1(self) | Deleted
FunLora_6_read(self) | Done | read(self)
FunLora_5_readString(self) | Deleted
TimeStamp(self) | Deleted

## Issue Tracker
Issue Tracker
Number | Priority | Status | Issue | Solve
1 | Low | Solved | In function __init__(), not sure if attributes a1 is used | unsused
2 | Low | Ongoing | Make an interface for function listPorts() | Make function displayPorts()
3 | Mid | Ongoing | Need a function checkCRC()
4 | Mid | Ongoing | Add attributes to LoRa, baudrate
5 | Mid | Ongoing | Add attributes to LoRa, ChipID
6 | Low | Ongoing | Interrupt findLoRa() if it takes too long to load
7 | Mid | Ongoing | Add attributes to LoRa, SerialPort
8 | Mid | Ongoing | Reconsider return value of getLoRaID(), hex or string?
9 | Mid | Ongoing | In function findLoRa(), change checking LoRa port method to __testIfLoRa()
10 | Low | Ongoing | In function findLoRa(), recheck raise OSError
11 | Low | Ongoing | In function getLoRaID(), change method to get the data byte
12 | Low | Ongoing | In getLoRaID(), sendByteToChip(), make a function specially for read and write byte
13 | Mid | Ongoing | In sendByteToChip() timeout statement recheck
14 | Low | Solved | Rearrange getLoRaID()
15 | High | Ongoing | Determine timesleep()

## Function Dependency
Number | Function | Dependency
0 | openPort
1 | closePort | setStandby
0 | serialWrite
0 | __calCRC
0 | check_header
4 | findLoRa | openPort | pingLoRa | check_header | closePort
1 | sendByteToChip | serialWrite
2 | pingLoRa | __calcCRC | sendByteToChip
0 | getLoRainfo
2 | resetLoRa | __calcCRC | sendByteToChip
2 | getStatus | __calcCRC | sendByteToChip
2 | setRx | __calcCRC | sendByteToChip
2 | setTx | __calcCRC | sendByteToChip
2 | setStandby | __calcCRC | sendByteToChip
2 | setSleep | __calcCRC | sendByteToChip
3 | get | __calcCRC | sendByteToChip | check_header
2 | readCounter | __calcCRC | sendByteToChip
3 | put | __calcCRC | sendByteToChip | check_header
1 | write | put
2 | read | readCounter | get
listPorts